## 🔹 Backend Development Milestone Breakdown

Technology Stack: Node.js (Express.js), MongoDB, AWS Hosting, WebSocket, and REST APIs
Total Cost (Backend Only): ₹5,95,000 + Taxes
Timeline: 70–80 Working Days
Payment Structure: 30% – 40% – 30%

### Milestone 1: Backend Foundation & Core Framework Setup (30%)

Duration: ~20–25 Working Days
Payment: ₹1,78,500 + Tax

#### Scope of Work

This milestone establishes the entire backend architecture — the backbone of the Gully Fame ecosystem — ensuring secure, modular, and scalable development practices.

Key Deliverables:

- Project Setup

  - Node.js + Express.js boilerplate with modular architecture (MVC pattern)

  - API routing and middleware setup (JWT, role-based authentication)

  - Environment configurations for DEV, QA, and PROD

- Database Design & Configuration

  - Schema creation in MySQL/MongoDB

  - Entities include:

    - Users (Fans, Entertainers, Sponsors, Admin)

    - Profiles, Content, Stories, Contests, Transactions, Subscriptions, Tips, Votes

  - Relation and indexing setup for optimized query performance

- Authentication & Authorization

  - JWT token system for multi-role access

  - Role-based routing (Admin, Fan, Entertainer, Sponsor)

  - Secure KYC data storage and encryption for personal documents

- API Structure

  - Base CRUD APIs (User Registration, Login, Profile CRUD)

  - API versioning setup (v1 base route)

  - Integration-ready endpoints with Flutter & React clients

- Core Utility Modules

  - OTP service integration (Firebase/MSG91)

  - Email and notification utility (NodeMailer + FCM tokens)

  - Error handling, validation (Joi), and response standardization

#### Outcome

- Fully functional backend skeleton

- Live authentication system ready for frontend integration

- Verified and tested database structure supporting all entities

### Milestone 2: Functional Module Development (40%)

Duration: ~25–30 Working Days
Payment: ₹2,38,000 + Tax

#### Scope of Work

This milestone covers all functional APIs and logic for core business modules like Contests, Content Management, and Monetization.

Key Deliverables:

- User & Entertainer APIs

  - Profile CRUD, follower/following logic

  - Story upload, expiry logic (24 hrs auto delete)

  - Live streaming event creation via WebRTC API (Agora/AWS IVS)

  - Tipping and subscription APIs (with currency mapping – coins system)

- Content Management

  - Upload module (video compression, thumbnails)

  - Content moderation logic (auto + admin review)

  - Like, comment, and report system

  - Scheduled story posting and archiving APIs

- Contest System

  - Contest creation (Admin/Sponsor)

  - Entry APIs (Fan/Entertainer uploads + fee deduction)

  - Voting APIs (1 fan = 1 vote, rate-limiting)

  - Judging logic (Sponsor-scored entries + fan votes weightage)

  - Contest results and leaderboard system

- Monetization & Payments

  - Razorpay / PayU API integration

  - Coin wallet management (buy, tip, earn, redeem)

  - Subscription management (monthly/weekly)

  - Withdrawals and admin approval APIs

  - Transaction history module (both ends)

- Notification & Real-Time System

  - Socket.io / WebSocket-based event push (live tipping, contest updates)

  - FCM integration for mobile notifications

#### Outcome

- All core modules are API-ready for integration.

- Verified payment and contest logic.

- Functional communication between fans, entertainers, and sponsors.

- Database records, security layers, and validations implemented.

### Milestone 3: Admin & Analytics Backend + QA & Optimization (30%)

Duration: ~20–25 Working Days
Payment: ₹1,78,500 + Tax

#### Scope of Work

This milestone focuses on admin control systems, analytics, and final optimization before deployment.

Key Deliverables:

- Admin Dashboard Backend

  - User management (activate/deactivate/verify)

  - Contest & transaction overview APIs

  - Content moderation approval/rejection

  - Reporting APIs for tips, subscriptions, and engagement

- Sponsor Dashboard APIs

  - Contest creation and tracking

  - Prize distribution logic

  - Sponsor analytics (views, entries, brand reach)

- Analytics Engine

  - Metrics like:

    - Engagement rate (views, likes, tips per entertainer)

    - Conversion ratio (free → subscribed users)

    - Contest participation rate

    - Average earning per entertainer (RpCH – Revenue per Contest Hour)

  - Real-time stats using aggregation pipelines

- Security & Optimization

  - Data sanitization, API rate limiting

  - Caching (Redis)

  - Backup automation and API performance optimization

- Testing & Integration

  - API testing (Postman suite)

  - End-to-end QA with Flutter and React frontend

  - API documentation (Swagger / Postman Collection)

#### Outcome

- Fully functional and integrated backend environment.

- Complete analytics reporting for admins and sponsors.

- Stable, optimized, and tested APIs ready for deployment.

### Deployment & Handover (Post Milestone Phase)

Deliverables:

- AWS Deployment (EC2, S3, CloudFront, RDS)

- Domain setup & SSL integration

- Environment migration (DEV → PROD)

- Admin panel + API documentation handover

- 7-day post-deployment support for issue resolution

### ✅ Summary Table

| Milestone | Scope | Timeline | Payment % | Amount (₹) |
| --- | --- | --- | --- | --- |
| M1 – Backend Foundation | Auth, DB, API Base, Core Setup | 20–25 Days | 30% | ₹1,78,500 |
| M2 – Core Functional Modules | Content, Contest, Payments, Monetization | 25–30 Days | 40% | ₹2,38,000 |
| M3 – Admin & Analytics | Admin, Sponsor, Reports, QA, Security | 20–25 Days | 30% | ₹1,78,500 |
| Post-Milestone (Deployment) | Deployment + Support | — | — | — |
| Total (Excl. Taxes) | — | 70–80 Working Days | 100% | ₹5,95,000 + Tax |